## August 2017
Date | Name | Project | Task | Start time | End time | Status | Comment
04.08.2017 | Harihara prabu U | After Hours - Key Releases |  | 11.00AM | 01.30 PM | Completed | Configuring my computer to the new hardware ESP8266 took a bit time.
Practising
Programming with ESP8266 and Arduino
|  |  | Programming with ESP8266 and Arduino by sending data to the server using POST | 03.00 PM | 06.45 PM | Completed | Was a bit difficult process. Completed with Muthu's support.
07.08.2017 | Harihara prabu U | After Hours - Key Releases | Study of MQTT | 10.30 AM | 12.30 PM | Completed | MQTT was studied and the concept was known clearly.
|  |  | Configuration of files for implementing MQTT | 12.30 PM | 01.30 PM | Completed | Successfully configured.
|  |  | Implementation of MQTT with Arduino and ESP8266 | 02.30 PM | 05.30 PM | In Progress | Was a bit difficult. Need Muthu's support. Will get clear by the next day.
|  |  | Controlling of LED using Arduino and ESP8266 through Smartphone | 05.30 PM | 06.45 PM | Completed | Completed Successfully.
08.08.2017 | Harihara prabu U | After Hours - Key Releases | Research in the existing Arduino projects and components | 10.30 AM | 01.30 PM | Completed | Was going through the existing projects to understand the coding better.
|  |  | Getting Started with Rasperry Pi | 02.45 PM | 04.00 PM | In Progress | Need Rasperry Pi OS from Muthu
|  |  | Research about the 4G LTE component LE910 AU | 04.00 PM | 07.00 PM | Completed | Need Rasperry Pi OS from Muthu
09.08.2017 | Harihara prabu U | After Hours - Key Releases | Research about LE910 AU -v2 , 4G LTE bands, Telstra mobile networks | 10:30 | 13:30 | Completed | Needed for the project to proceed.
|  |  | Testing LE910 AU and working with it for sending SMS | 14:30 | 19:00 | In progress | Problem with the SIM registration. Posted the trouble on their forum. Waiting for their reply towards it.
10.08.2017 | Harihara prabu U | After Hours - Key Releases | Working with LE910 AU-v2 for sending SMS | 10:30 | 14:00 | In Progress | No reply from their forum. Their employees are on holidays.
|  |  | Working with LE910 AU-v2 for sending SMS and researching about anyother compatible product | 15:00 | 19:00 | In Progress | No alternative products found
11.08.2017 | Harihara prabu U | After Hours - Key Releases | Getting Lists and Discussion with Muthu | 10:00 | 11:30 | Completed | Got the list of components status
|  |  | Working with GSM Receiver to send SMS | 11:30 | 14:00 | In Progress | Working on it
|  |  | Working with GSM Receiver to send SMS | 15:00 | 19:30 | In Progress | The given SIM is not working with GSM receiver and the SIM card holder is needed.
12.08.2017 | Harihara prabu U | After Hours - Key Releases | Working with GSM Receiver to send SMS | 10:30 | 14:00 | Completed | The SMS was sent by GSM receiver.But, it takes prolonged time to deliver. For eg: half -an-hour.
|  |  | Checking with LE910 AU-v2 for outer coverage | 15:00 | 18:30 | Completed | Even when it was checked in the open area, it failed to work
14.08.2017 | Harihara prabu U | After Hours - Key Releases | Going through existing project code | 10:15 | 13:45 | Completed | Some existing code were being studied.
|  |  | Working with GSM shield to receive SMS | 15:00 | 19:00 | In Progress | Facing some trouble to receive SMS
17.08.2017 | Harihara prabu U | After Hours - Key Releases | Working with GSM shield to receive SMS | 10:15 | 13:45 | In Progress | No sending or receiving of SMS
|  |  | Working with GSM shield to receive SMS | 14:45 | 16:15 | Completed | For sending or receiving SMS, we need to have a 2G SIM card, or else we need to buy a new GSM shield which supports all types of SIM
|  |  | Working with LE910AU-v2 from the suggestion of cookinghacks.com | 16:30 | 19:00 | Completed | It gives a different error and we posted the same on the forum.
18.08.2017 | Harihara prabu U | After Hours - Key Releases | Preparation of Case Study for AHKR | 10:30 | 14:00 | In Progress | Creating the case study for AHKR
|  |  | Preparation of Case Study for AHKR | 15:00 | 19:00 | Completed | Case study prepared
21.08.2017 | Harihara prabu U | After Hours - Key Releases | Working with Raspberry Pi with Monitor | 10:30 | 13:00 | Completed | Raspberry Pi working fine
|  |  | Working with Raspberry Pi connected with laptop | 14:00 | 19:00 | Completed | Raspberry Pi working fine
22.08.2017 | Harihara prabu U | After Hours - Key Releases | Learning Python | 10:15 | 12:00 | In Progress | Learnt the basics
|  |  | R&D for Raspberry Pi 3 | 12:00 | 13:30 | In Progress | Taken the code for app generation
|  |  | Working in Android Studio & with LE910 | 14:30 | 19:00 | Completed | Built the app and tested LE910
23.08.2017 | Harihara prabu U | After Hours - Key Releases | Setting up system after Ubuntu installed | 10:30 | 14:00 | Completed | Installing and configuring to work in Ubuntu
|  |  | R&D for SMS API | 15:30 | 19:00 | Completed | The flow has been taken and need to implement
24.08.2017 | Harihara prabu U | After Hours - Key Releases | Sending an SMS via API through Arduino | 10:15 | 13:45 | Completed | This methoad gives a lots of errors, which seems to be unclear. Hence, failed.
|  |  | Making the Arduino as a Web socket | 14:45 | 19:15 | Completed | R&D is over. And implementation begins and it’s quite difficult to configure the system.
28.08.2017 | Harihara prabu U | After Hours - Key Releases | Configuring systems for nodejs and npm | 10:30 | 14:00 | Completed | Configuration over and demo works
|  |  | Making the Arduino as a Web socket | 15:00 | 18:00 | In Progress | Started with customization
31.08.2017 | Harihara prabu U | After Hours - Key Releases | Checking with LE910 AU-v2 as said by the forum | 10:15 | 12:30 | Completed | The setup was made and no response from the device.
|  |  | Making the Arduino as a Web socket | 12:30 | 13:45 | In Progress | Making Arduino as a web socket.
|  |  | Making the Arduino as a Web socket | 14:45 | 19:00 | Completed | The arduino is now made to work as a web socket

## September'17
Date | Name | Project | Task | Start time | End time | Status | Comment
01.09.2017 | Harihara prabu U | After Hours - Key Releases | Checking with LE910 AU-v2 and research about SMS API | 11:00 | 14:00 | Completed | The LE910’s working is replied to the forum. SMS API ‘s are taken from Twilio
|  |  | SMS API research and Learning of PHP | 16:30 | 19:00 | Completed | The SMS API’s are to be worked with PHP. So, learning PHP.
04.09.2017 | Harihara prabu U | After Hours - Key Releases | R&D of SMS API | 10:15 | 13:30 | Completed | Full research into Twilio SMS processes
|  |  | Checking with LE910 AU-v2 and Making Arduino Websocket demo | 14:30 | 19:00 | Completed | Demo is ready and LE910 has to be repaired by cookingHacks
05.09.2017 | Harihara prabu U | After Hours - Key Releases | Learning of Django and Python | 10:15 | 13:30 | Completed | Django configuration is over.
|  |  | Creating a demo app in Django | 14:30 | 19:00 | In progress | Creating a web application for voting polls.
06.09.2017 | Harihara prabu U | Pooja Essentials | Pooja Essentials – KT | 11:00 | 14:00 | Completed | Understanding of the project Pooja Essentials
|  |  | Learning of MVC and Opencart | 16:00 | 19:00 | Completed | MVC in PHP and opencart have been studied.
07.09.2017 | Harihara prabu U | Pooja Essentials | Configuring system for Opencart | 10:00 | 14:00 | In progress | Configuration includes downloading and installing of apache, xampp and curl to use in.
|  |  | Configuring system for Opencart | 15:00 | 19:00 | In progress | System got crashed, when installing.
08.09.2017 | Harihara prabu U | Pooja Essentials | Taking system backup and setting temporary system | 10:00 | 13:00 | Completed | System backup has been made and got access to temporary system
|  |  | Learning Opencart documentation | 13:00 | 14:00 | Completed | Went through the documentation of Opencart
|  |  | Documentation | 15:00 | 16:30 | In progress | Documenting about Pooja Essentials
|  |  | Project Discussion | 16:30 | 18:00 | Completed | Knowledge Transfer and discussion regarding AHKR & Pooja Essentials
|  |  | Documentation about Pooja Essentials | 18:00 | 19:00 | In progress | Documenting about Pooja Essentials
11.09.2017 | Harihara prabu U | Pooja Essentials | Prepared the BRD of Pooja Essentials | 11:00 | 14:00 | Completed | Prepared the Business requirements & documents of Pooja Essentials.
|  | AHKR | Setting up the system | 15:00 | 16:00 | Completed | Newly installed OS. So, installed needed softwares.
|  |  | Twilio configuration settings | 16:00 | 17:00 | Completed | Twilio needed some additional configuration to work in Nodejs.
|  |  | Sending SMS using twilio and Nodejs | 17:00 | 19:00 | Completed | Customised to send SMS using Nodejs
18.09.2017 | Harihara prabu U | After Hours - Key Releases | Receiving SMS using Twilio | 10:00 | 13:30 | In progress | For receiving SMS through Twilio, we should enable the permission from network operator.
|  |  | Checking with other API – textlocal | 14:30 | 16:00 | Completed | They doesn’t suit our requirements.
|  |  | Installing Django, Mysql and python for checking Web application | 16:00 | 19:00 | Completed | For knowing the status of the web application, these have been installed and checked.
19.09.2017 | Harihara prabu U | After Hours - Key Releases | Analysing AHKR Web application | 10:15 | 11:00 | Completed | The modules were correct and need help to undergo the remaining tasks.
|  |  | Checking with Twilio and Airtel for SMS | 11:00 | 12:00 | Completed | We need to pay for the service to reply back to the SMS
|  |  | Installing Arduino and checking for Nodejs compatibility | 12:00 | 12:45 | Not completed | Checking for the integration of Arduino with Nodejs
|  |  | Checking with Twilio for SMS support | 12:45 | 13:45 | Completed | Twilio doesn’t offer two-way SMS in India. Hence, we can’t use Twilio
|  |  | R&D with Textlocal SMS API | 14:45 | 16:30 | Completed | Textlocal SMS API is compatible to use in India. It can be used to reply also.
|  |  | Discussion with Kalai on AHKR Web application | 16:30 | 17:30 | Completed | Key status module has to be created with Django.
|  |  | Discussion about New project – Trading platform | 17:30 | 18:30 | Completed | Discussion about the new product
|  |  | Installation of XAMPP | 18:30 | 19:15 | Completed | Installed XAMPP.
20.09.2017 | Harihara prabu U | Trading – R&D | R&D about Trading, Stock Exchange and Multicharts | 10:15 | 12:00 | Completed | Got a clear idea for starting with charts.
|  |  | R&D about charts open-source project | 12:00 | 14:00 | Completed | Got some open-source projects about charts
|  |  | Implementing the open-source API | 15:00 | 16:30 | Completed | Implemented Techan.JS with the data from csv file
|  |  | R&D about other trading platforms and live data streaming | 16:30 | 19:00 | In progress | Doesn’t have a clear idea of real time data transfer
21.09.2017 | Harihara prabu U | Trading – R&D | Implementing open source API for charting | 10:15 | 14:00 | Completed | Implementing the open source projects for charting
|  |  | Documentation, Review and customization of charting | 15:00 | 19:30 | Completed | Documentation of R&D and review with Ramkumar
22.09.2017 | Harihara prabu U | AHKR | Creation of key status model in AHKR web application | 10:15 | 12:30 | Completed | Completed the key status model
|  |  | Review | 12:30 | 14:00 | Completed | Review over and document submitted
|  |  | Getting help from Deepak & Kalai for creating custom admin | 15:00 | 18:00 | In progress | While getting fixido project KT, sql server not working properly. Can’t able to fix that issue
25.09.2017 | Harihara prabu U | AHKR | Configuring system for Fixido | 10:15 | 14:00 | In progress | Installed Mysql Workbench and moved the fixido project to my system
|  |  | Configuring system for Fixido | 15:00 | 19:00 | In progress | Creating virtual environment and installing all the requirements, still the project fails to run.
26.09.2017 | Harihara prabu U | Fixido and AHKR | Configuring and learning about Fixido | 10:15 | 14:00 | Completed | Fixido had been run in my local environment and studied
|  |  | Developing AHKR web application | 15:30 | 19:30 | Completed | AHKR Web application has been created and testing has to be done
27.09.2017 | Harihara prabu U | AHKR | Issue resolving – Getting usertypes | 10:15 | 14:00 | Completed | Issue resolved
|  |  | Issue resolving – Displaying the current user data & tested with test cases | 15:00 | 19:00 | Completed | Issue resolved and Tested
28.09.2017 | Harihara prabu U | AHKR | Module for hitting URL to send SMS and logging in to the web application | 10:15 | 14:00 | Completed | Functions for hitting URL to send SMS and send key status to the AHKR web application
|  |  | Module for hitting URL to send SMS and logging in to the web application | 15:00 | 17:30 | In progress | Completed the functions
|  |  | Detecting the key motion | 17:30 | 19:00 | Not completed | PIR sensor is not working fine. Need to be replaced

## October'17
Date | Name | Project | Task | Start time | End time | Status | Comment
03.10.2017 | Harihara prabu U | After Hours - Key Releases | System Repairing | 10:15 | 11:15 | Completed | System shows a No signal message on monitor. Fails to continue further. Re-assembled CMOS and RAM and works fine
|  |  | Automatic opening and closing of box | 11:15 | 13:30 | In progress | Using stepper motors, trying to open and close a box
|  |  | Automatic opening and closing of box | 14:30 | 17:00 | Completed | Now, the box opens and closes automatically using stepper motor
|  |  | Interfacing Wemos D1 Mini with Arduino Mega | 17:00 | 19:00 | Completed | Googling the interfacing connections of Wemos D1 Wifi module with Arduino Mega. Seems to be difficult
04.10.2017 | Harihara prabu U | After Hours - Key Releases | Full function with only Wemos D1 mini | 10:15 | 12:30 | Completed | Without Arduino, all the data is being programmed at Wemos D1 mini
|  |  | Solving MySql ERROR | 12:30 | 13:30 | Not resolved | Unable to access mysql client & server
|  |  | Solving MySql ERROR | 14:30 | 16:30 | Solved | Tried possible solutions, re-installing mysql client & server works fine. But, still unable to install workbench
|  |  | Integrating Full modules and testing and demo to kalai | 16:30 | 19:00 | Completed | Integrated all the modules and tested with minimum test cases. Demo shown to Kalai.
05.10.2017 | Harihara prabu U | After Hours - Key Releases | Setting up for video and capturing | 10:15 | 12:30 | Completed | Some modules weren’t working as expected. So, corrected them and captured a video
|  |  | Video editing and adding subtitles | 12:30 | 13:30 | In progress | Video has to be edited and subtiltles have to be added for a clear understanding
|  |  | Video editing and adding subtitles | 14:30 | 15:30 | Completed | Video has been edited and subtitles are added
|  |  | Installing workbench and making it to work properly | 15:30 | 16:30 | Completed | Mysql workbench has been installed and working fine
|  |  | Working on Senthil’s computer to resolve issue on Mysql | 16:30 | 19:00 | Not resolved | Mysql workbench has been installed and fails to work with client
06.10.2017 | Harihara prabu U | After Hours - Key Releases | Editing video for AHKR | 10:30 | 13:30 | Completed | Video has been edited and got approval
|  |  | Documentation of AHKR Demo video | 14:30 | 19:00 | Completed | Documentation has bee done and sent to Deepak.
09.10.2017 | Harihara prabu U | Mobile App with Azure as backends service | KT of Microsoft Azure as a backend service for Mobile apps | 10:15 | 11:00 | Completed | KT of Android Mobile App with Microsoft Azure as backends service
|  |  | Checking for stable android version and Microsoft Azure | 11:00 | 13:30 | Completed | Android 2.3.3 is found to be the latest and stable versions
|  |  | Installing Android Studio in Linux and creating account in Microsoft Azure | 14:30 | 16:30 | Completed | Installed Android Studio and created an acoount for Microsoft Azure
|  |  | Testing a demo app (To-do list) with Microsoft Azure as backends service | 16:30 | 19:15 | Completed | Successfully created an app (to-do list) with Microsoft Azure as backends service
10.10.2017 | Harihara prabu U | R&D on Microsoft Azure | Meeting | 10:30 | 11:45 | Completed | Regarding the new project
|  |  | R&D on Microsoft Azure components | 11:45 | 13:45 | Completed | R&D on Microsoft Azure and its components were done
|  |  | Documentation of Microsoft Azure | 14:45 | 19:00 | Completed | Documentation on Microsoft Azure has been done.
11.10.2017 | Harihara prabu U | R&D on Android Studio | Installing and checking Android Studio Preview 3 | 10:15 | 12:30 | Completed | It doesn’t have any features like Visual Studio
|  |  | Learning about Design Patterns | 12:30 | 13:30 | Completed | To start coding in Java, we should know about design patterns in Java.
|  |  | Learning about DAO design pattern and inspecting the To-do list Android app | 14:30 | 19:00 | Completed | Checking the code of the To-do list and its execution
12.10.2017 | Harihara prabu U | Learning Android Studio | Android Studio tutorials | 10:15 | 13:45 | Completed | Watched the Android Studio tutorial videos and documents
|  |  | Android Studio tutorials | 14:45 | 15:30 | Completed | Learning about UI of Android Studio
|  |  | Discussion | 15:30 | 17:00 | Completed | Discussion on the platform and concepts
|  |  | Microsoft Azure MFA | 17:00 | 19:00 | Completed | MFA authentication is not possible on Microsoft Azure for Mobile Apps.
13.10.2017 | Harihara prabu U | Research on Microsoft Azure on Android app | Microsoft Azure components | 10:15 | 13:45 | Completed | Research on Microsoft Azure components to be used.
|  |  | Research on existing Android projects and Android Studio Preview 3. | 14:45 | 16:30 | Completed | Research on existing Android projects and Android preview3 tool to use.
|  |  | Creating concepts and documenting them | 16:30 | 18:30 | Completed | The concepts to be developed are converted into words and documented them.
16.10.2017 | Harihara prabu U | Research on Microsoft Azure on Android app | Creating models for Mahindra Quotation app | 10:15 | 13:30 | Completed | Creating prototypes for Mahindra app
|  |  | Diwali celebration | 14:30 | 19:00 | Completed | Diwali celebration
20.10.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Creation of BRD for the Mahindra car service centre app | 10:15 | 14:00 | In progress | Creating BRD for the Mahindra app.
|  |  | Lunch Break | 14:00 | 15:00 | Completed | Lunch
|  |  | Creation of BRD for the Mahindra car service centre app | 15:00 | 16:30 | Completed | Creating BRD for the Mahindra app.
|  |  | Design of the database | 16:30 | 18:30 | Completed | Some modifications were done and yet to be confirmed
|  |  | Discussion | 18:30 | 20:45 | Completed | Discussion on the concept flow and DB design
23.10.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Creating databases in Microsoft Azure | 10:15 | 14:00 | Completed | Databases have been created in Microsoft Azure and dumps file is being sent to Kalai for verification
|  |  | Checking how to create connect database with the mobile service | 15:00 | 17:00 | Completed | Connected the database with the Mobile service and it’s ready to use.
|  |  | Checking how to integrate the code with the Mobile services backend | 17:00 | 19:00 | Completed | Some configuration parameters have to be included to make the app work in our own project.
24.10.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Correction of database | 10:15 | 14:00 | Completed | Correcting database by initializing auto-increment primary key. Installed SSMS and made corrections.
|  |  | Connecting Microsoft Azure with Android | 15:00 | 19:00 | Completed | Connections were made from Microsoft Azure to Android
25.10.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Issue in connecting database to Android | 10:15 | 14:15 | In progress | Insertion of data in the database is causing some error
|  |  | Issue in connecting database to Android | 15:15 | 16:30 | Completed | Issue Resolved. Insertion of data is made possible.
|  |  | Creating Login page and adding functionality | 16:30 | 20:15 | Not completed | Just the checking of data has to be made.
26.10.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Creating Login page and adding functionality | 10:15 | 12:30 | Completed | Login page is working fine and tested with Kalai
|  |  | Designing toolbar | 12:30 | 13:30 | In progress | Designing a custom toolbar for the application.
|  |  | Designing toolbar | 14:30 | 19:30 | In progress | Designing a custom toolbar for the application.
27.10.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Designing toolbar | 10:15 | 14:15 | In progress | Designing a custom toolbar for the application.
|  |  | Designing toolbar | 15:15 | 19:15 | Completed | Designed a custom toolbar for the application.
28.10.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Working in Service Dashboard screen | 10:15 | 14:00 | Completed | Worked in Service Dashboard screen and completed the screen.
|  |  | Working in Complaints screen | 15:00 | 20:00 | In progress | Working in Complaints screen.
29.10.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Worked in Complaints screen | 15:00 | 18:00 | Completed | Completed Login, New service, complaints and toolbar and pushed in git.
30.10.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Clearing sessions in the app | 10:15 | 12:00 | Completed | Cleared the sessions in the app.
|  |  | Working in Complaints screen | 12:00 | 14:00 | Completed | Inserting and deleting records as per the checkboxes
|  |  | Receiving notifications | 15:00 | 19:00 | Not completed | Facing some issues while trying to start a new activity from the notification.
31.10.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Receiving notifications | 10:15 | 13:30 | Completed | Created a link to notification to open the activity
|  |  | Creating manager screen | 14:30 | 19:00 | Completed | Created the manager screen and a link to the notification
02.11.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Creating manager dashboard | 10:15 | 13:30 | Not completed | Testing has to be done.
|  |  | Creating new account in Azure and database | 14:30 | 19:45 | Completed | Database is not connected to App services. Facing some issues.

## November'17
Date | Name | Project | Task | Start time | End time | Status | Comment
02.11.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Creating manager dashboard | 10:15 | 13:30 | Not completed | Testing has to be done.
|  |  | Creating new account in Azure and database | 14:30 | 19:45 | Completed | Database is not connected to App services. Facing some issues.
03.11.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Creating new database and database connection | 10:15 | 12:30 | Completed | Created the new database and database connection in Microsoft Azure.
|  |  | Working in manager Dashboard | 12:30 | 14:00 | In Progress | Working in manager dashboard screen.
|  |  | Working in manager Dashboard | 15:00 | 17:30 | Not completed | Some issues have been found. Not rectified.
|  |  | Generating apk and recording video for Serapp | 17:30 | 20:30 | Completed | Video has been recorded and video can’t be exported since it’s cracked version.
06.11.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Resolving system boot up issue | 10:15 | 10:45 | Completed | Dismantled RAM and inserted. Worked fine
|  |  | Working in manager Dashboard screen | 10:45 | 13:45 | In Progress | Working in manager dashboard screen.
|  |  | Working in manager Dashboard screen | 14:45 | 16:00 | Completed | Resolved the issue in manager dashboard screen.
|  |  | Working for Auto complete Search box | 16:00 | 19:15 | Completed | The search box will autocomplete the typed keyword in the search box in New Service screen.
07.11.2017 | Harihara prabu U | Mahindra Car service centre app with Microsoft Azure as backend service | Research on Microsoft Azure components | 10:15 | 13:30 | Completed | Read the current Azure components and its applications.
|  |  | Issue in manager Dashboard | 14:30 | 17:15 | Completed | After pulling, some conflicts occured with other pages. Resolved them.
|  |  | Issue in manager Screen and notifications and testing | 17:15 | 19:25 | Completed | All conflicts were resolved and app submitted to Kalai for verification.
08.11.2017 | Harihara prabu U | Home Automation | Home automation configuration | 10:15 | 13:45 | Not completed | Running Node js creates some problem and not working fine.
|  |  | Home automation configuration | 14:45 | 16:30 | Not completed | Some issues have been found. Not rectified.
|  | MRV | Making Video for MRV | 16:30 | 19:45 | Not Completed | System down.
09.11.2017 | Harihara prabu U | MRV | Making Video for MRV – editing | 10:15 | 12:30 | Completed | Video made and been exported to Kalai
|  | Home Automation | Home automation configuration | 12:30 | 13:30 | Not Completed | Some issues have been found. Not rectified.
|  |  | Home automation configuration | 14:30 | 19:30 | Not Completed | Some issues have been found. Not rectified. Trying with Raspberry
10.11.2017 | Harihara prabu U | Home Automation | Home automation configuration in Raspberry Pi | 10:15 | 13:45 | Completed | Node js and NPM were configured in Raspberry Pi
|  |  | Home automation configuration | 14:45 | 19:40 | Completed | Configured and hosted. But, video hasn’t been recorded.
13.11.2017 | Harihara prabu U | Oozaaoo | Creation of Oozaaoo project in Django- Tour package | 10:30 | 13:30 | Completed | Completed the Django tour package model
|  |  | Creation of booking module | 14:30 | 16:30 | Completed | Completed the booking model
|  | Home Automation | Home automation configuration | 16:30 | 19:00 | In Progress | Connection needs transistor to work properly.
14.11.2017 | Harihara prabu U | Home Automation | Home automation Configuration and video recording | 10:15 | 12:30 | Completed | Still editing has to be done and subtitles have to be added to the video.
|  | Oozaaoo | Creating user roles in Oozaaoo | 12:30 | 13:45 | In Progress | Started to create the user roles
|  | MRV | MRV- screenshots | 14:45 | 16:30 | Completed | Took screenshots of Azure & source code and submitted.
|  | Oozaaoo | Creating user roles in Oozaaoo | 16:30 | 19:00 | In Progress | Some issues have been found. Not rectified.
15.11.2017 | Harihara prabu U | Home Automation | Video editing for Home Automation | 10:15 | 13:30 | Completed | Video has been recorded and submitted.
|  | Oozaaoo | Creating tour package and users model | 14:30 | 19:00 | Completed | Created the users and tour package model
16.11.2017 | Harihara prabu U | Oozaaoo | Checking user roles and changing admin template theme | 10:15 | 13:45 | Completed | Checking for the user roles consistency and changed the exisiting template theme.
|  | MRV | Azure Documentation on MRV | 14:45 | 18:00 | Completed | Documentation on Azure and submitted to Kalai.
|  |  | Video recording on MRV | 18:00 | 19:00 | In Progress | Connecting more than 1 device makes the server hang on. Switching to Raspberry Pi and hosting the same.
17.11.2017 | Harihara prabu U | Home Automation | Home Automation Configuration in Raspberry Pi | 10:15 | 12:30 | Completed | Servers hosted in Raspberry Pi can able to connect more than 1 device.
|  | MRV | R&D in App Updation in Azure | 12:30 | 13:30 | In Progress | Usually, app updation would happen in Google play store. App updation in Azure is in reserch.
|  | New idea | Discussion about Android app. | 14:30 | 16:00 | Over | Need to submit POC at next week.
|  | MRV | R&D in App Updation in Azure | 16:00 | 17:00 | In Progress | Still not yet came to a conclusion
20.11.2017 | Harihara prabu U | Food delivery app | Analysis on Food delivery app | 10:15 | 13:45 | Completed | Analysed aasife briyani site and created the modules.
|  |  | Discussion regarding DB design. | 14:45 | 18:00 | Completed | Came out with different scenarios and had some changes in DB design.
|  |  | Modifying DB design | 18:00 | 19:15 | Completed | Modified the DB design and reviewed with Kalai.
22.11.2017 | Harihara prabu U | Food delivery app | Creating DB and models | 10:15 | 11:30 | In Progress | Creating the models and database
|  |  | Meeting | 11:30 | 12:00 | Completed | Regarding office timings.
|  |  | Creating DB and models | 12:00 | 13:30 | In Progress | Creating the models and database
|  | MRV | Checking for viewing databases in PHP | 14:30 | 19:00 | Completed | Can’t create the database view in PHP using Azure without any drivers.
23.11.2017 | Harihara prabu U | MRV | Checking for viewing data in website through PHP | 10:30 | 13:30 | In Progress | Tried in windows system by installing the required drivers.
|  |  | Checking for viewing data in website through PHP | 14:45 | 17:00 | Completed | Doesn’t workout as the versions had some problems with the drivers in PDO.
|  |  | Checking for viewing data in website through Nodejs | 17:00 | 19:15 | Completed | Database is connected through Nodejs. Need to display it in a website.
24.11.2017 | Harihara prabu U | MRV | Creating a nodejs server script to view the tables from Azure database | 10:15 | 13:30 | In Progress | Brought the data from server to the client side. Need to couple it with UI.
|  |  | Creating a nodejs server script to view the tables from Azure database | 14:30 | 17:00 | In Progress | Brought the data from server to the client side. Need to couple it with UI.
|  | Presentation | Presentation(activity) | 17:00 | 19:00 | Done | Presentation activity
27.11.2017 | Harihara prabu U | MRV | Viewing the Azure database in a separate website | 9:30 | 14:00 | In Progress | Brought the data to the client side for viewing
|  |  | Viewing the Azure database in a separate website | 15:00 | 18:30 | In Progress | All tables have been displayed and data tables could not been applied.
28.11.2017 | Harihara prabu U | MRV | Viewing the Azure database in a separate website | 9:30 | 12:30 | In Progress | The data tables styling alone has not applied
|  |  | Discussion | 12:30 | 13:30 | Done | Discussion regarding the work schedule of the current week.
|  |  | Viewing the Azure database in a separate website | 13:30 | 14:15 | In Progress | The data tables styling alone has not applied
|  |  | Viewing the Azure database in a separate website | 15:15 | 17:30 | Completed | css alone not applied and gave to Kalai for verification
|  |  | MRV – app flow documentation | 17:30 | 18:30 | Completed | The app flow has been documented and waiting for the review.
29.11.2017 | Harihara prabu U | MRV | Data and account Migration in Azure | 10:00 | 13:45 | Completed | A new account has been created and database has been migrated to the new account.
|  |  | Changes in Android source code | 14:45 | 16:00 | Completed | Modifications in the android source code are completed.
|  | Oozaaoo | Oozzaoo model changes | 16:00 | 18:30 | In Progress | Oozaaoo changes in the table have been created.
|  | MRV | Creating notification hub in Azure account | 18:30 | 19:00 | In Progress | Created the notification hub account and configured.
30.11.2017 | Harihara prabu U | MRV | Configuring notification in Android source code and generating apk | 10:15 | 11:15 | Completed | Configured the notification setting credentials with the Android app.
|  | Oozaaoo | Working in Oozaaoo for form changes | 11:15 | 13:45 | In Progress | Tried for creating database and error occured.
|  |  | Working in Oozaaoo for form changes | 14:45 | 19:00 | In Progress | Tried for creating database and error occured.
01.12.2017 | Harihara prabu U | Oozaaoo | Working in Oozaaoo for form changes | 10:00 | 13:45 | In Progress | Mapping fields for merging models.
|  |  | Working in Oozaaoo for form changes | 14:45 | 19:30 | In Progress | Facing some issues. Need to resolve them

## December 2017
Date | Name | Project | Task | Start time | End time | Status | Comment
01.12.2017 | Harihara prabu U | Oozaaoo | Working in Oozaaoo for form changes | 10:00 | 13:45 | In Progress | Mapping fields for merging models.
|  |  | Working in Oozaaoo for form changes | 14:45 | 19:30 | In Progress | Facing some issues. Need to resolve them
04.12.2017 | Harihara prabu U | Oozaaoo | Working in Oozaaoo for form changes | 10:00 | 13:45 | In Progress | Created the separate models
|  |  | Working in Oozaaoo for form changes | 14:45 | 16:30 | In Progress | Created the separate models
|  |  | Working in Oozaaoo for form changes | 16:45 | 19:00 | Completed | Created the separate models and need to incorporate the jQuery plugin.
05.12.2017 | Harihara prabu U | Energysoft | KT for Anand | 10:15 | 13:45 | Completed | KT about Django for Anand.
|  |  | Creating models for energysoft | 14:45 | 19:00 | In Progress | Created the models for energysoft. Some of the models need explanation.
06.12.2017 | Harihara prabu U | Energysoft | Discussion on creating models | 10:00 | 14:00 | Completed | Discussion went and finalized the models to be created.
|  |  | Analyzing and searching source code for app implementations. | 17:30 | 20:00 | In Progress | Source code has been taken and some were implemented.
07.12.2017 | Harihara prabu U | Energysoft | Analyzing and searching source code for app implementations. | 10:00 | 13:45 | In Progress | Source code has been taken and some were implemented.
|  |  | Analyzing and searching source code for app implementations. | 14:45 | 19:30 | In Progress | Source code has been taken and some were implemented.
20.12.2017 | Harihara prabu U | Energysoft | Worked on Notifications page | 11:00 | 14:00 | In Progress | Waiting for the API and format.
|  |  | Worked on Gallery page | 15:00 | 19:35 | In Progress | Working on the Gallery to be in a single page
21.12.2017 | Harihara prabu U | Energysoft | Worked on Gallery page | 10:00 | 13:45 | In Progress | Working on the Gallery to be in a single page
|  |  | Worked on Gallery page | 14:45 | 19:30 | Completed | Main gallery and event gallery has been completed without backend connection.
27.12.17 | Harihara prabu U | Energysoft | Package name changes and generation of APK | 14:30 | 16:45 | Completed | Package name has been changed and apk also generated.
|  |  | Analyzing of API’s to be done | 17:00 | 19:15 | Completed | API’s completed has been listed out and sent.
28.12.2017 | Harihara prabu U | Energysoft | Working on gallery page | 10:45 | 13:45 | In Progress | Working on the single page gallery for events & news
|  |  | Working on gallery page | 14:45 | 19:00 | Completed | Finished working on gallery and helped Ravi on build.gradle issues.
29.12.2017 | Harihara prabu U | Energysoft | Working on lists on fragment | 14:45 | 19:15 | In Progress | Facing some issues. Need to resolve them
30.12.2017 | Harihara prabu U | Energysoft | Working on lists on fragment | 11:30 | 14:30 | In Progress | Fixed the issue and applying the list to all fragments.
|  |  | Working on lists on fragment | 15:30 | 16:45 | Completed | Applied the lists to all fragments.
|  |  | Working in Change Password form | 16:45 | 17:45 | In Progress | Authenticator is not recognizing and yet to finish.

## January 2018
Date | Name | Project | Task | Start time | End time | Status | Comment
02.01.2018 | Harihara prabu U | Energysoft | Developing social media pages (FB & Twitter) | 10:50 | 14:00 | Completed | Created two pages Facebook & Twitter
|  | MRV | Creating document on concept of MRV | 15:00 | 16:30 | Completed | Submitted the document on the concept of MRV.
|  | Energysoft | Working on shoutout pages | 17:00 | 18:00 | In Progress | API for getting employees tag is pending and hence not completed.
|  | MRV | Corrections on the document of MRV | 18:00 | 19:40 | Completed | Made some corrections and submitted the document.
03.01.2018 | Harihara prabu U | Energysoft | Working on Feedback, Banner, Gallery | 14:45 | 18:30 | Completed | Completed all the pages with backend.
|  |  | Working on shoutout page | 18:30 | 19:40 | In Progress | Some issues are being faced. Have to resolve them.
04.01.2018 | Harihara prabu U | Energysoft | Worked on Shoutout list, post, upcoming birthday & anniversary | 18:45 | 20:30 | In Progress | Shoutout list Api is not working. Shoutout post is completed. Upcoming birthday & anniversary are completed. Today birthday & anniversary are yet to complete
05.01.2018 | Harihara prabu U | Energysoft | Worked on Upcoming birthday & anniversary | 11:00 | 13:45 | Completed | Upcoming birthday & upcoming anniversary were integrated and also the individual birthday also integrated.
|  |  | Worked on Shoutout lists & gallery | 15:00 | 19:30 | Completed | Still, splitting of comma generated gallery images were pending
08.01.2018 | Harihara prabu U | Energysoft | Worked on Events Full Listing with image slider as new fragment | 10:30 | 13:45 | In Progress | Facing some issues, while working with fragment for image sliding.
|  |  | Worked on Events Full Listing with image slider as new fragment | 15:00 | 17:30 | Completed | Resolved the issue and still layout has to be designed well. Informed Ravi regarding on that & working towards it.
|  |  | Worked on Notification List and Displaying full content | 17:30 | 19:40 | Completed | Notification has been listed and still testing is pending with all data.
09.01.2018 | Harihara prabu U | Energysoft | Testing and fixing on Notification List | 10:30 | 13:45 | Completed | Some issues have been faced. Fixed them.
|  |  | Worked on CEO post page | 15:00 | 16:30 | Completed | Completed posting the CEO message with the list
|  |  | Worked on CEO listing page | 16:30 | 17:00 | In Progress | Working with the list
|  |  | Discussion regarding MRV | 17:00 | 18:30 | Completed | Discussion over and need to do R&D in them
|  |  | Worked on CEO listing page | 18:30 | 19:30 | Completed | Completed the list
10.01.2018 | Harihara prabu U | Energysoft | Working on the Polls | 10:35 | 14:00 | In Progress | Working on the voting and listing questions.
|  |  | Working on the Polls | 16:30 | 19:00 | Completed | Completed and revoting is alone pending.
17.01.2018 | Harihara prabu U | MRV | Checking of Chrome on Android devices | 10:15 | 13:30 | In Progress | Android devices doesn’t support other mobile device on chrome.
|  |  | Checking of Chrome on Laptop | 14:40 | 19:15 | Completed | Laptops support all mobile devices on chrome. Mobile also captures laptop and vice versa. Tested and verified.
18.01.2018 | Harihara prabu U | MRV | Checking for Bluetooth classic devices supportivity in Chrome | 10:15 | 13:30 | In Progress | Chrome won’t support bluetooth classic devices.
|  |  | Checking for hybrid apps & native apps security | 14:45 | 19:20 | Completed | Whatever be the apps hybrid or native, apk’s can be reverse engineered.
19.01.2018 | Harihara prabu U | MRV | Checking for Bluetooth classic devices supportivity in Chrome | 10:15 | 11:45 | Completed | Chrome won’t support bluetooth classic devices.
|  |  | Review meeting | 11:45 | 13:45 | Completed | Discussion over
|  |  | Checking for hybrid apps security | 14:45 | 19:00 | Completed | Progaurd can be applied to reduce the reverse engineering effect.
22.01.2018 | Harihara prabu U | MRV | Checking for bluetooth compatibility | 14:40 | 15:30 | Completed | Chrome won’t support bluetooth classic devices.
|  | Energysoft | Generation of new apk with updated files | 15:30 | 19:00 | Completed | Generated new apk and sent to Madhivanan.
23.01.2018 | Harihara prabu U | Energysoft | Uploading new apk to the play store | 10:05 | 13:30 | Completed | Uploaded the new apk to the google play store.
|  |  | Implementing search functionality | 14:30 | 19:05 | In Progress | Integrating the search API with the apk.
30.01.2018 | Harihara prabu U | Energysoft | Vdart – Checking code | 10:05 | 11:00 | In Progress | Checked the issues and planned to resolve them.
|  | MRV | Checking for NDK support on decompiling | 11:00 | 13:30 | In Progress | Checked whether the source code is able to decompile.
|  |  | Bluetooth connectivity | 14:30 | 19:15 | Completed | Source code has been generated and yet to test in car.
01.02.2018 | Harihara prabu U | MRV | OBD scanning | 13:30 | 19:15 | Completed | Need to test it once, before it’s deployed
07.02.2018 | Harihara prabu U | Energysoft | Vdart – issue fixing | 11:20 | 13:45 | Completed | Issue fixing
|  |  | Vdart – issue fixing | 14:45 | 19:30 | Completed | Completed and published at the play store.
08.02.2018 | Harihara prabu U | Oozaaoo | Discussion on Oozzaaoo | 11:00 | 13:30 | In Progress | Discussion regarding the modules of Oozzaaoo
|  |  | Discussion on Oozzaaoo | 14:30 | 19:30 | Completed | Discussion regarding the modules of Oozzaaoo
09.02.2018 | Harihara prabu U | Oozaaoo | Installing Django and finalising models | 10:30 | 14:00 | In Progress | Installed Django in the system and partiallly finalised the models.
|  |  | Creating models on Django | 15:00 | 19:45 | In Progress | Created models on Django for some modules.
12.02.2018 | Harihara prabu U | Energysoft | Fixing issues in Vdart | 10:45 | 13:45 | In Progress | Fixing issue in Mobile app(Profile & gallery)
|  |  | Fixing issues in Vdart | 16:00 | 19:10 | Completed | Fixing issue in Mobile app(Home page)
14.02.2018 | Harihara prabu U | Energysoft | Installing Django in laptop | 11:15 | 14:00 | Completed | Installed Django, Python & Mysql.
|  |  | Auto saving form | 15:00 | 19:15 | Completed | Auto saving of form from marketing to booking.

## March 2018
Date | Name | Project | Task | Start time | End time | Status | Comment
14.03.2018 | Harihara prabu U | Energysoft | Fixing bugs | 10:05 | 1:30 | Completed | Tried refresh and failed,
|  | MRV | Fixing bugs | 2:45 | 19:00 | Completed | Submitted the apk for testing
15.03.2018 | Harihara prabu U | MRV – IVN | Discussion | 11:00 | 14:00 | Completed | Discussed and created modules and ready for documenting.
|  | Energysoft | Fixing bugs | 15:00 | 19:00 | Completed | Fixed bugs and submitted for testing
16.03.2018 | Harihara prabu U | Energysoft | Dialog box showups | 10:00 | 14:00 | Completed | Completed in the home page and submitted for testing.
|  |  | Modifying event date & time | 15:00 | 19:00 | Completed | Completed and uploaded to play store for release.
19.03.2018 | Harihara prabu U | Self-learning | Learning javascript design patterns | 10:05 | 13:30 | In Progress | Some of the design patterns and concepts in js were studied.
|  |  | Solving problems in hackerrank | 15:00 | 19:00 | Completed | Solved some algorithmic problems in hackerrank.
20.03.2018 | Harihara prabu U | Energysoft | Notification changes and bug fixes | 9:40 | 13:30 | Completed | Notification message was changed and uploaded to play store.
|  | Oozaaoo | Updation in Oozaaoo | 14:30 | 18:45 | In Progress | Two tickets were closed and three were pending.
21.03.2018 | Harihara prabu U | Oozaaoo | Redefining Coordination model | 10:30 | 13:45 | Completed | Coordination model is done.
|  |  | Export as csv | 14:45 | 19:15 | In Progress | Exporting as csv doesn’t work. Need to do research.
27.03.2018 | Harihara prabu U | Energysoft | Recent news issue fixing | 10:05 | 13:30 | In Progress | Source code changes weren’t reflected at android emulator. Issue fixed.
|  |  | Recent news issue fixing | 14:30 | 16:30 | Completed | Recent news issue fixed.
|  | Oozaaoo | Export as csv | 16:30 | 19:00 | In Progress | Found the source code. Need to implement them.